{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["공사","용역","물품"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":0,"comments":9,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"공사","index":0,"n_rows":10,"n_cols":20,"rows_kept":10,"cut":false,"hidden":false,"merged":[[1,1,1,19]],"flags":["formulas_cached_only"]}
[]
[null,"2014년도 당진시 분기별 발주계획"]
[{"$nulls":19},"(단위 : 백만원)"]
[null,"발주연도","발주분기","발주월","발주방식","사 업 명","공 종","계약방법","도급액","관급자재비","기 타","계","금차도급금액","국고보조금액","예산코드(17자리)","부 서 명","담당자","전화번호","협정여부","비 고"]
[null,2014,1,1,"자체발주","삽교호 서해안권 광역관광개발사업(토목,건축)","토건","일반",2864,1194,0,4058,1798,2029,null,"지역자원조성과","오주원",3504774,"비협정"]
[null,2014,1,1,"자체발주","삽교호 서해안권 광역관광개발사업(전기)","전기","수의",85,210,1,296,60,148,null,"지역자원조성과","\"","\"","비협정"]
[null,2014,1,1,"자체발주","기지시줄다리기박물관  상설전시실  개편공사","건축","수의",18,0,0,18,"-",0,"-","지역자원조성과","고대영",4782,"비협정","명시이월사업"]
[null,2014,1,2,"자체발주","기지시줄다리기박물관 체험학습 전기간선 공사","기타","수의",22,0,0,22,"-",0,"-","지역자원조성과","“","“","비협정"]
[null,2014,1,3,"자체발주","기지시줄다리기박물관 야외공연장 보수공사","건축","일반",23,0,0,23,"-",0,"-","지역자원조성과","“","“","비협정","명시이월사업"]
[null,2014,2,5,"자체발주","기지시줄다리기박물관 지열냉난방 노후 배관 교체공사","기타","수의",40,0,0,40,"-",0,"-","지역자원조성과","“","“","비협정"]

{"sheet":"용역","index":1,"n_rows":9,"n_cols":20,"rows_kept":9,"cut":false,"hidden":false,"merged":[[1,1,1,19]],"flags":["formulas_cached_only"]}
[]
[null,"2014년도 당진시 분기별 발주계획"]
[{"$nulls":19},"(단위 : 백만원)"]
[null,"발주연도","발주분기","발주월","발주방식","사 업 명","공 종","계약방법","도급액","관급자재비","기 타","계","금차도급금액","국고보조금액","예산코드(17자리)","부 서 명","담당자","전화번호","협정여부","비 고"]
[null,2014,1,1,"자체발주","삽교호 해안탐방로 해역이용협의","전문","수의",22,0,null,22,22,11,null,"지역자원조성과","오주원",3504774,"비협정"]
[null,2014,1,1,"자체발주","삽교호 서해안권광역관광개발사업 폐기물처리","기타","일반",76,0,null,76,76,38,null,"지역자원조성과","오주원",3504774,"비협정"]
[null,2014,1,2,"자체발주","삽교호 호수공원 조성사업 기본 및 실시설계","기타","일반",90,0,null,90,90,45,null,"지역자원조성과","오주원",3504774,"비협정"]
[null,2014,1,2,"자체발주","체류형 관광숙박단지 지장물조사","기타","수의",17,null,null,17,17,0,null,"지역자원조성과","박현진",3504773,"비협정"]
[null,2014,1,1,"자체발주","시립박물관 진입도로 개설 도시관리계획(도시계획시설) 결정(변경) 용역","기타","일반",70,0,0,70,"-",0,"-","지역자원조성과","김유상",4781,"비협정"]

{"sheet":"물품","index":2,"n_rows":5,"n_cols":20,"rows_kept":5,"cut":false,"hidden":false,"merged":[[1,1,1,19]],"flags":["formulas_cached_only"]}
[]
[null,"2014년도 당진시 분기별 발주계획"]
[{"$nulls":19},"(단위 : 백만원)"]
[null,"발주연도","발주분기","발주월","발주방식","사 업 명","공 종","계약방법","도급액","관급자재비","기 타","계","금차도급금액","국고보조금액","예산코드(17자리)","부 서 명","담당자","전화번호","협정여부","비 고"]
[null,2014,1,3,"자체발주","기지시줄다리기박물관 강의용 책상, 의자구입","기타","수의",5,0,0,5,"-",0,"-","지역자원조성과","고대영",4782,"비협정"]