{"text_format":"2","workbook":"xls","n_sheets":2,"sheets":["공사","용역"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":0,"comments":6,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"공사","index":0,"n_rows":12,"n_cols":20,"rows_kept":12,"cut":false,"hidden":false,"merged":[[1,1,1,19]],"flags":["formulas_cached_only"]}
[]
[null,"2014년도 당진시 분기별 발주계획"]
[{"$nulls":19},"(단위 : 백만원)"]
[null,"발주연도","발주분기","발주월","발주방식","사 업 명","공 종","계약방법","도급액","관급자재비","기 타","계","금차도급금액","국고보조금액","예산코드(17자리)","부 서 명","담당자","전화번호","협정여부","비 고"]
[null,2014,1,"2월","조달발주","당진청소년 문화의집 증축","건축","일반",null,null,null,200,null,null,null,"여성가족과","이상민",3712,"비협정"]
[null,2014,1,"3-4월","조달발주","청소년 수련원 내부안전시설 보수","건축","일반",null,null,null,200,null,null,null,"여성가족과","이상민",3712,"비협정"]
[null,2014,1,"2월","자체발주","남부권 공설묘지 배수로 공사","토목","수의",null,null,null,20,null,null,null,"여성가족과","김금식",3704,"비협정"]
[null,2014,1,"3-4월","조달발주","석문공설묘지 관리사 신축","건축","일반",null,null,null,300,null,null,null,"여성가족과","김금식",3704,"비협정"]
[{"$nulls":11},0]
[{"$nulls":11},0]
[{"$nulls":11},0]
[{"$nulls":11},0]

{"sheet":"용역","index":1,"n_rows":12,"n_cols":20,"rows_kept":12,"cut":false,"hidden":false,"merged":[[1,1,1,19]],"flags":["formulas_cached_only"]}
[]
[null,"2014년도 당진시 분기별 발주계획"]
[{"$nulls":19},"(단위 : 백만원)"]
[null,"발주연도","발주분기","발주월","발주방식","사 업 명","공 종","계약방법","도급액","관급자재비","기 타","계","금차도급금액","국고보조금액","예산코드(17자리)","부 서 명","담당자","전화번호","협정여부","비 고"]
[null,2014,1,null,"자체발주","청소년 수련시설 건축물 석면조사","기타","수의",null,null,null,0,4,{"$nulls":5},"비협정"]
[{"$nulls":11},0]
[{"$nulls":11},0]
[{"$nulls":11},0]
[{"$nulls":11},0]
[{"$nulls":11},0]
[{"$nulls":11},0]
[{"$nulls":11},0]